## Slide 1: Bray Team Week 8 Update
Avery Haynes, Locke Lehmann, Travis Carlson, Cody Sims, Zachary Walker, Michael Hager
3/18/2024

## Slide 2: Weekly Deliverables
Tasks | Lead | Percentage Done | Notes
Begin potentiometer validation testing | Avery/Locke | 80% | Just need to test in the valve
Build frame for valve and actuator and motor mount | Cody/Travis | 80% | Motor mounted just need to complete valve mount
Implement sensors into system | Zack | 50% | Successfully have drilled into stop bolts.
Wire sensors into DAQ and computer | Michael | 100% | Completed.
Test Hall effect sensor | Locke/Travis | 25% | Made design, received sensor, must print test rig using new circuit board.

## Slide 3: Purchasing Updates
Recently ordered Hall Effect Expansion Board ($16)
Will purchase materials for building testing rigs from Home Depot
Budget Update: $807.57 spent (out of $3,803 approved)
Notes: Done - Avery 2/18

## Slide 4: Potentiometer
ADC Chips soldered and connected to the Raspberry Pi
Can now read Potentiometer to an exact degree of rotation instead of just analog

## Slide 5: Strain Gauges
Cylindrical Strain gauges from HBK arrived
With some guidance from FEDC staff made nice drills
Next step - epoxy sensors into bolts

## Slide 6: Adhesives
EP 70 Comp A&B
Registered with the FEDC and is in the chemical cabinet, must have proper PPE to use
Looking to use this week to install strain gauges into stop bolts

## Slide 7: Hall effect sensor testing apparatus
Found expansion circuit board that will connect the A1335 rotary hall effect sensor to the Raspberry Pi
Next step - Modify and print the test rig according to the new board specifications

## Slide 8: Motor Bracket
Motor mounted to actuator and ball valve system
Machined connecting slit to attached to the stem
Soldered wires for motor to connect to the Pi.

## Slide 9: Positioner
Able to power with a DC power supply set to 4-20mA
Completed to last stage of calibration. Need to hook up to shop air in order to complete calibration
Learned how to navigate the menu and different settings

## Slide 10: Remaining Validation
Receive and print 2nd iteration of hall effect test rig.
Begin testing with potentiometer in the valve.
Start measuring time and voltage to see if a correct estimate of torque can be made.
Inquire with the FEDC on the proper environment to use the adhesives in and equipment that is needed.

## Slide 11: Gantt Chart

## Slide 12: Next Week's Deliverables
Tasks | Lead | Percentage Done | Notes
Begin potentiometer validation testing | Avery/Locke | 50% | Ready for testing.
Test motor system | Cody/Travis | 50% | Motor mounted into the stem of the actuator. And wired to the Pi
Implement strain gauges into stop bolts | Zack | 25% | Talk with FEDC about PPE and space.
Prep Hall effect sensor Test | Locke/Travis | 25% | Made design, received sensor, must print test rig using new circuit board.