## Gantt Chart
MEEN 401 - 900
PROJECT TITLE |  | Embedded Valve & Actuator Sensors |  |  |  |  | COMPANY NAME | [6 empty] | Bray
PROJECT TEAM |  | Avery Haynes, Cody Sims, Locke Lehmann, Michael Hager, Travis Carlson, Zachary Walker |  |  |  |  | DATE | [6 empty] | 2023-08-21
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | MEEN 401
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Weekly Meeting Presentations
| Week 2 | Cody Sims | 2023-08-21 | 2023-08-28 | 7 | 100% | bar: WEEK 1 M to WEEK 2 M
| Week 3 | Cody Sims | 2023-08-28 | 2023-09-04 | 6 | 100% | bar: WEEK 2 M to WEEK 3 M
| Week 4 | Cody Sims | 2023-09-04 | 2023-09-11 | 7 | 100% | bar: WEEK 3 M to WEEK 4 M
| Week 5 | Cody Sims | 2023-09-11 | 2023-09-18 | 7 | 100% | bar: WEEK 4 M to WEEK 5 M
| Week 6 | Cody Sims | 2023-09-18 | 2023-09-25 | 7 | 100% | bar: WEEK 5 M to WEEK 6 M
| Week 7 | Cody Sims | 2023-09-25 | 2023-10-02 | 7 | 100% | bar: WEEK 6 M to WEEK 7 M
| Week 8 | Cody Sims | 2023-10-02 | 2023-10-09 | 7 | 100% | bar: WEEK 7 M to WEEK 8 M
| Week 9 | Cody Sims | 2023-10-09 | 2023-10-16 | 7 | 100% | bar: WEEK 8 M to WEEK 9 M
| Week 10 | Cody Sims | 2023-10-16 | 2023-10-23 | 7 | 10% | bar: WEEK 9 M to WEEK 10 M
| Week 11 | Cody Sims | 2023-10-23 | 2023-10-30 | 7 | 0% | bar: WEEK 10 M to WEEK 11 M
| Week 12 | Cody Sims | 2023-10-30 | 2023-11-06 | 6 | 0% | bar: WEEK 11 M to WEEK 12 M
| Week 13 | Cody Sims | 2023-11-06 | 2023-11-13 | 7 | 0% | bar: WEEK 12 M to WEEK 13 M
| Week 14/15 | Cody Sims | 2023-11-13 | 2023-11-20 | 7 | 0% | bar: WEEK 13 M to WEEK 14 M
Design Reports / Presentations
| DR1 Draft / Presentation | All | 2023-08-28 | 2023-09-11 | 13 | 100% | bar: WEEK 2 M to WEEK 4 M
| DR1 Final | All | 2023-09-18 | 2023-10-02 | 14 | 100% | bar: WEEK 5 M to WEEK 7 M
| DR2 / Presentation | All | 2023-10-16 | 2023-10-30 | 14 | 20% | bar: WEEK 9 M to WEEK 11 M
| DR3 / Presentation | All | 2023-11-20 | 2023-12-04 | 14 | 0% | bar: WEEK 14 M to WEEK 15 F
Bray Meetings
Research