## Sheet1
Project Team Name: Bray Team - Embedded Valve and Actuator Sensors
Team Members: Michael Hager, Avery Haynes, Cody Sims, Locke Lehmann, Travis Carlson, Zachary Walker
Attribute | Embodiment Design Checklist Item | % Complete | Status of Design | Unresolved Issues | Get well plans | Expected Resolution Date
Function | Are the customer needs satisfied, as measured by the target values? Is the stipulated product architecture and function(s) fulfilled? What auxiliary or supporting functions are needed? | 0 | As of now, the group has not begun prototype testing. Although it has been verified through initial validation testing that the rotary potentiometer will give adequate position readings, that is as far as the group has gone. | The group is still waiting on material delivery and a complete experimental testing plan. Pending a meeting with Bray (2/5), the group should finish their test plans and begin experimenting with possible solutions. This item will ultimately be complete when testing is complete and results are presented for approval to Bray. | Recieve necessary testing items from vendors and Bray. Complete testing plans | 2024-03-31
Working Principles and Form solutions | Do the chosen form solutions (architecture and components per function) produce the desired effects and advantages? What disturbing noise factors may be expected? What byproducts may be expected? | 15 | Tested rotary potentiometer in the FEDC labs with the team to observe the error when calculating degrees of rotation given voltage readings. Waiting on parts from Amazon to implement sensors into. | Physical implementation of sensors into parts. Currently waiting for parts to arrive. | We already have a space in the labs reserved, so we plan to immediately begin testing around with materials once they arrive. | 2024-02-18
Layout, Geometry, and Materials | Do the chosen layout, component shapes, materials, and dimensions provide minimal performance variance to noise (robustness), adequate durability (strength), efficient material usage (strength to mass ratio), suitable life (fatigue), permissible deformation (stiffness), adequate force flows (interfaces and stress concentrations), adequate stability, impact resistance, freedom from resonance, unimpeded expansion and heat transfer, and acceptable corrosion and wear with the stipulated service life and loads? | 50 | The valves and actuators are already known to be able to withstand factory conditions, since they have already been mass produced and tested by Bray. The sensors will not be subjected to fluid flo so that is not a concern, but the ambient conditions could have an effect. | Need to test sensor solutions in different environments of temperature and pressure to ensure they don't break down in harsher conditions. | Will use a combination of Bray's and A&M's facilities in order to test this. | 2024-03-24
Energy and Kinematics | Do the chosen layout and components provide efficient transfer of energy (efficiency), adequate transient and steady state behavior (dynamics and control across energy domains), and appropriate motion, velocity, and acceleration profiles? | -- | Criterion not applicable to our design project. The scope of our design involves using sensors to measure the performance and dynamics of preexisting systems, not to improve them. |  |  | --
Safety | Have all of the factors affecting the safety of the user, components, functions, operation, and the environment been taken into account? | 30 | The group does not anticipate extensive safety precautions being necessary for testing a prototype. Although some systems will be pressurized, the group will assess the appropriate amount of pressure put into the prototypes during the experimental design. Proper PPE will be worn in the FEDC to protect eyes, ears, and body. | A proper safety plan will be attached to the testing plan that will consider the specifications of each valve/actuator and compressors or other equipment being used. | Every member of the group will need to be familiar with the codes applicable to our field of design as well as safety procedures when operating each device in the experiment. | 2024-02-10
Ergonomics | Have the human.. machine relationships been fully considered? Have unnecessary human stress or injurious factors been predicted and avoided? Has attention been paid to aesthetics and the intrinsic "feel" of the product? | 75 | These parts mostly work in automated manner in a factory or processing site, and the installation of the valves and actuators has already been developed by Bray for existing products. | Possibly the implementation of the sensors into the valves and actuators for production. | Bray will handle production problems after the project is over, as they don't want that to be in the scope of our project. | 2024-02-17
Production | Has there been a technological and economic analysis of the production processes, capability, and suppliers? | 50 | Bray handles production of valves and actuators already, and we are working mainly with their R&D department so they have informed us that they don't want us to really be concerned with production methods or things like that, | N/a | We will hand over our finished prototypes to Bray and they will handle the implementation process into their products, since they want us to focus on design and accuracy. | 2024-03-24
Quality Control | Have standard product tolerances been chosen (not too tight)? Have the necessary quality checks been chosen (type, measurements, and time)? | 60 | Standard tolerances for our solutions have been set after discussing them with Bray. | Need to test sensors with parts one they come in and see if pressure affects the accuracy of sensor measurements. | Test sensors and accuracy once parts arrive in our designated work area in the FEDC. | 2024-03-10
Assembly | Can all internal and external assembly operations be performed simply, repeatably, and in the correct order (without ambiguity)? Can components be combined (minimize part count) without affecting modular architectures and functional independence of the product? | 15 | The connections between the components have been considered in the placement of sensors, but not all sensors have been received and placed on the valve or actuator yet. | Interactions between the two sensors (position and torque) are considered unlikely to affect each other but combined testing is necessary in order to prove this. | Plan is in place to test solutions separately on the valve and actuator, and then combine the two components to ensure the solutions do not interfere with each other. | 2024-03-24
Transport | Have the internal and external transport conditions and risks been identified and solved? Have the required packaging and dunnage been designed? | 20 | There has been a need identified to place a metal seal around the potentiometer at the bottom of the valve, to conform to valve standards. | This will have to be accomplished after the initial testing of the potentiometer solution, to determine if that is the best solution and if a seal is necessary. | If a rotary potentiometer is selected, then we will consult with Bray on the best method to seal the system so it conforms to flow standards and can be produced. | 2024-03-24
Operation | Have all of the factors influencing the product's operation, such as noise, vibration, and handling, been considered? | 20 | Product should be able to operate in normal function of any valve & actuator environments. Sensors selected currently show no concerns with operation in vibrating or hot environments. | More validation testing is required to determine the total constraints of the sensors used in the valve & actuator system. | Design & perform more experiments throughout Spring semester to validate design solutions | 2024-03-10
Lifecycle | Can the product, its components, its packaging be reused or recycled? Have the materials been chosen and clumped to aid recycling? Is the product easily disassembled? | 30 | Exact operation configuration of product has not been finalized, but the product should be easily disassembled as our sensor system must be encased into the valve and actuator. | Determining exact material to be used to enclose the sensors & data aquisition system onto the final product. | protyping case materials & consulting with Bray regarding their default choices. | 2024-02-28
Maintenance | Can maintenance, inspection, repair, and overhaul be easily performed and checked? What features have been added to the product to aid in maintenance? | 30 | The products selected for the sensors have been estimated to have longer lifespans than the valves and actuators they are used in, so that a failing sensor is not inaccurately diagnosed as a failing valve. | Lifetime testing will be difficult to perform without automated valve-testing equipment, which is located at Bray and not mobile. | If there is time at the end of the project we could do some lifetime testing at Bray, if not, we will give them our prototype for them to do further lifetime testing on it at their facility after the project ends. | 2024-03-24
Costs | Have the stipulated cost limits been observed? Will additional operational or subsidiary costs arise? | 70 | Bray has provided more materials than expected that do not count against our budget. This has provided some 'wiggle room' in the types of sensors we can purchase & quantity | Selecting the exact sensors for Hall effect and strain gauges that are available with convenient suppliers, determining how often we are traveling to Houston this Spring | Look through current suppliers and select sensors that will meet product requirements, consult with Bray on sensor selection. | 2024-02-12
Schedules | Have the delivery dates be met, including tooling? What design modifications might reduce cycle time and improve delivery? | 25 | Experienced slight delay in the delivery of sensors due to miscommunication with purchasing office. The team will now be able to start testing throughout the upcoming weeks. Gantt chart has been updated accordingly. | Must complete deliverables efficiently to make up for lost time. | Stick to the updated Gantt chart and stay up to date on project deliverables as well as class deliveables. | 2024-02-23