## Sheet1
Product Name | Bray Valve and Actuator Smart System | Development Team Avery Haynes, Locke Lehmann, Cody Sims, Travis Carlson, Michael Hager, Zach Walker |  |  |  | Page No |  | XX of YY
System Name | Valve Position Measurement |  |  |  |  | FMEA Number
Subsystem Name | Potentiometer for position measurement |  |  |  |  | Date
Component Name
Part # and Functions | Potential Failure Mode | Assessment | [6 empty] | Recommended Actions |  | Action Results
|  | Potential Effect(s) of Failure | Severity (S) | Potential Causes and Mechanisms of Failure | Occurence (O) | Current Design Controls Test | Detection (D) | RPN | Description of Action | Responsibility & Target Completion Date | Actions Taken | Sev (S) | Occ (O) | Det (D) | RPN
Potentiometer Sensor embedded into underside of ball valve | Potentiometer head breaks off of sensor body | Sensor head causes a jam in the ball valve operation | 8 | Assembly error; sensor not directly in line with ball rotation axis | 3 | Lifetime cycle testing, verify measurements before drilling, verify drill spots before sensor insertion | 2 | 48 | Ensure high-precision mill and accurate measurements before drilling into valve casing | Cody Sims, 2/28/24
|  | Potentiometer stops transmitting position data to end-user | 9 | Part error; poorly manufactured sensor or defective | 2 | Research effectiveness of selected sensor, its lifetime, and operating conditons | 2 | 36 | Lifecycle test of potentiometer prior to embedding in valve | Michael Hager, 2/28/24
|  | Sensor head damages exterrior casing of valve | 3 | Environmental error; operation temperature or pressure causes degredation to the part over time | 4 | Lifetime cycle testing in ambient conditions | 2 | 24 | Lifecycle test of potentiometer prior to embedding in valve | Michael Hager, 2/28/24
Cylindrical strain gauge embedded into the stop bolts of the actuators | Strain gauge cannot withstand force of actuator | Strain gauge falls out of stop bolt | 7 | addeshive used is not strong enough | 4 | use recommended adhesive with the strain gauge and life time test with millions of actuations | 4 | 112 | ensue proper amount of adhessive is applied by practicing on extra bolts before using the actual stop bolts | Locke Lehmann (3/10/24)
|  | Strain gauge breaks | 8 | Too Much actuation force | 3 | Test design between 40 psi and max of 80 psi | 5 | 120 | Use larger-sized stop bolts so that there is more metal between the sensor and the stop bolt | Locke Lehmann (3/26/24)
|  | stain gauge oreintated imporporly in stop bolt | 8 | incorrect implentation of strain gauge or strain gauge wrong size for stop bolt. | 3 | follow instructions and communicated with company on size needed with the dimensions of the stop bolts | 3 | 72 | Contact supplier and provide schematics to get best bolt size. Also recieve insertion instructions and follow them carefully | Avery Haynes (3/10/24)
Motor attached to the raspberry PI ADC converter chip and actuation stem | Bad MotorEMF data | Rasberry Pi is not able to read motor EMF data | 8 | ranges of voltages is measured when one consistent voltage is needed | 6 | Fast actuation time so little variance can happen, Attached as close to the stem to reduce mechanical noise | 4 | 192 | get higher-quality motor that will spin more consistently over time. Use the least amount of mechanical interations to connect to the stem.
|  | Torque error greater than 5% | 9 | motor used outputs inconsitant voltages between each trial | 4 | record each voltage value and compare them to previos trials at the same conditions | 2 | 72 | get higher quality motor that has better quality bushing and will output consistant voltages over multiple trials. Use the least amiount of mechanical interations to connect to the stem.
|  | The motor does not rotate the same amount as the actuator | 7 | adhesive between metal and plastic is not strong enough | 3 | Use eyes to see if the plastic gear is slipping. Do this by making marks and see if the gear is rotating the full 90 degrees as it should. | 3 | 63 | use a gear that screws into the hole on the actuator shaft
hall effect sensor placed under a magnetic feild | Cannot sense magnet feild accuratly | position error greater than 2% | 9 | Magnetic properties of the valve casing interferes with magnetic feild | 4 | test with magnetic interference to determine how to position sensor with realtion to sensor device | 5 | 180 | cut a hole between sensor element and magnet so there is not direct internference between them. (can use potentiometer hole) | Cody sims (2/21/24)
|  | no signal outputted from the sensor | 9 | Magnet to far from hall effect sensor, or magnet not strongh enough | 4 | test distances from magnet to sensor to determine the sensing range of the hall effect sensor | 4 | 144 | put magnet as close as posible but still keep the ball of the valve floating
Rasberry Pi collecting sensor data | resolution of data to imprecise | can not achieve desired accuracy due to measuring resolution | 5 | 10 bit processor cannot provide enough resolution for measurements. 0.4 increments | 10 | test linear potentiometer to see steps in increasing position | 3 | 150 | Buy 16 bit processesing chip that can achieve better resolution | Avery Haynes (2/21/24
|  | time measurement is not accurate due to low resolution | 7 | Pi can not keep track of time in small enough steps to be precise | 10 | strat and stop timmer in less than 1 second in small steps to see if we can get sunstially differnt times. | 4 | 280 | Buy 16 bit processesing chip that can achieve better resolution | Avery Haynes (2/21/24